## ST2 card power level
Node_Name | LEA | Platform | Type | Task | Priority | Start_Date | End_Date | Remark
CEN-OTNI-OSNT16-001 Shelf0-4-11ST2 | CEN | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OTNI-OSNT16-001Shelf0-12-13ST2 | CEN | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OTNI-OSNT16-001 Shelf0-4-11ST2 | WE | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OTNI-OSNT16-001 Shelf0-11-13ST2 | WE | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
AG-OTNI-OSNT16-001 Shelf0-3-13ST2 | AG | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
AW-OTNI-OSNT16-001 Shelf0-3-13ST2 | AW | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
GL-OTNI-OSNT16-001 Shelf0-3-13ST2 | GL | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
PTB-OTNI-OSNT16-001 Shelf0-3-13ST2 | PTB | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
RN-OTNI-OSNT16-001 Shelf0-3-13ST2 | RN | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
BS-OTNI-OSNT16-001 Shelf0-3-13ST2 | BS | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
BTP-OTNI-OSNT16-001 Shelf0-3-13ST2 | BTP | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
HO-OTNI-OSNT16-001 Shelf0-3-13ST2 | HO | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
UM-OTNI-OSNT16-001 Shelf0-3-13ST2 | UM | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
KT-OTNI-OSNT16-001 Shelf0-3-13ST2 | KT | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
KHN-OTNI-OSNT16-001 Shelf0-3-13ST2 | KHN | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
EMB-OTNI-OSNT16-001 Shelf0-3-13ST2 | EMB | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
TG-OTNI-OSNT16-001 Shelf0-3-13ST2 | TG | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MGE-OTNI-OSNT16-001 Shelf0-3-13ST2 | MGE | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OTNI-OSNT16-001 Shelf0-4-11ST2 | MV | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OTNI-OSNT16-001 Shelf0-12-13ST2 | MV | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
GKW-OTNI-OSNT16-001 Shelf0-3-13ST2 | GKW | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
KJ-OTNI-OSNT16-001 Shelf0-3-13ST2 | KJ | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OTNI-OSNT16-001 Shelf0-5-13ST2 | MH | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OTNI-OSNT16-001 Shelf0-4-13ST2 | MH | ITMC | OTN | Check optical power levels on ST-2 boards and escalate to relevant Network team | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE

## Ambient Temp
Node_Name | LEA | Platform | Type | Task | Priority | Start_Date | End_Date | Remark
CEN-ITMC | CEN | ITMC | NA | Check Ambient Environment and escalate to relevant teams | Med | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-ITMC | WE | ITMC | NA | Check Ambient Environment and escalate to relevant teams | Med | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE

## Auto Backup
Node_Name | LEA | Platform | Type | Task | Priority | Start_Date | End_Date | Remark
CEN-OSN9800-U32 | CEN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T64 | CEN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1A | CEN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1B | CEN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1E | CEN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1F | CEN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 2A | CEN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 2B | CEN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN9560 | CEN | ITMC | SDH | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN3500 | CEN | ITMC | SDH | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN2500 | CEN | ITMC | SDH | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN9800-U32 | WE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T64 | WE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1A | WE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1B | WE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1E | WE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1F | WE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 2A | WE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 2B | WE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN9560 | WE | ITMC | SDH | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN3500 | WE | ITMC | SDH | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T64 | MV | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T16 1A | MV | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T16 1B | MV | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T16 1E | MV | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T16 1F | MV | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T16 2A | MV | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T16 2B | MV | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN7500 | MV | ITMC | SDH | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN9800-U32 | MH | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN9800-U32 | MH | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN8800-T16 1A | MH | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN8800-T16 1B | MH | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN8800-T16 1E | MH | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN8800-T16 1F | MH | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN8800-T16 2A | MH | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN8800-T16- 2B | MH | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MH-OSN9560 | MH | ITMC | SDH | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Kalutara | KT | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Ambalangoda | AG | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Galle | GL | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Boralesgamuwa | BS | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Keselhenawa | KHN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Meegahathenna | MGE | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Batapola | BTP | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Udugama | UM | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Pitabeddara | PTB | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Kamburupitiya | KJ | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Homagama | HG | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Awissawella | AW | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Rathnapura | RN | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Godakawela | GKW | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Embilipitiya | EMB | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
Tangalle | TG | ITMC | OTN | Ensure that equipment data has been backed up to the NMS server | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to ITMC instead of relevant NWEE

## Manual Backup
Node_Name | LEA | Platform | Type | Task | Priority | Start_Date | End_Date | Remark
NCE-Server | NA | ITMC | Server | Manually backup NMS data and copy data to Intranet Shared folder | High | 2025-03-01 | 2025-03-08
NCE-Server | NA | ITMC | Server | Manually backup NE data and copy data to Intranet Shared folder | High | 2025-03-01 | 2025-03-08

## Rectifier Battery
Node_Name | LEA | Platform | Type | Task | Priority | Start_Date | End_Date | Remark
ITMC Rectifier Battery Bank-1 | CEN | ITMC | Battery | Check Rectifier Battery Voltages | High | 2025-03-01 | 2025-03-08
ITMC Rectifier Battery Bank-2 | CEN | ITMC | Battery | Check Rectifier Battery Voltages | High | 2025-03-01 | 2025-03-08

## Filter Cleaning
Node_Name | LEA | Platform | Type | Task | Priority | Start_Date | End_Date | Remark
CEN-OSN9800-U32 | CEN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T64 | CEN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1A | CEN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1B | CEN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1E | CEN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1F | CEN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 2A | CEN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 2B | CEN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN9560 | CEN | ITMC | SDH | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN3500 | CEN | ITMC | SDH | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN2500 | CEN | ITMC | SDH | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN9800-U32 | WE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T64 | WE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1A | WE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1B | WE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1E | WE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1F | WE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 2A | WE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 2B | WE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN9560 | WE | ITMC | SDH | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN3500 | WE | ITMC | SDH | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T64 | MV | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 1A | MV | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 1B | MV | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 1E | MV | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 1F | MV | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 2A | MV | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 2B | MV | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN7500 | MV | ITMC | SDH | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN9800-U32 | MH | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN9800-U32 | MH | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 1A | MH | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 1B | MH | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 1E | MH | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 1F | MH | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 2A | MH | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16- 2B | MH | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN9560 | MH | ITMC | SDH | Clean air filters | High | 2025-03-01 | 2025-04-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
Kalutara | KT | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Ambalangoda | AG | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Galle | GL | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Boralesgamuwa | BS | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Keselhenawa | KHN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Meegahathenna | MGE | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Batapola | BTP | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Udugama | UM | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Pitabeddara | PTB | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Kamburupitiya | KJ | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Homagama | HG | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Awissawella | AW | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Rathnapura | RN | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Godakawela | GKW | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Embilipitiya | EMB | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30
Tangalle | TG | ITMC | OTN | Clean air filters | High | 2025-03-01 | 2025-04-30

## Power supply and Grounding
Node_Name | LEA | Platform | Type | Task | Priority | Start_Date | End_Date | Remark
CEN-OSN9800-U32 | CEN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T64 | CEN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1A | CEN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1B | CEN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1E | CEN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 1F | CEN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 2A | CEN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN8800-T16 2B | CEN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN9560 | CEN | ITMC | SDH | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN3500 | CEN | ITMC | SDH | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
CEN-OSN2500 | CEN | ITMC | SDH | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN9800-U32 | WE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T64 | WE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1A | WE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1B | WE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1E | WE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 1F | WE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 2A | WE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN8800-T16 2B | WE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN9560 | WE | ITMC | SDH | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
WE-OSN3500 | WE | ITMC | SDH | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to ITMC instead of relevant NWEE
MV-OSN8800-T64 | MV | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 1A | MV | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 1B | MV | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 1E | MV | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 1F | MV | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 2A | MV | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN8800-T16 2B | MV | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Mount Lavinia CLS instead of relevant NWEE
MV-OSN7500 | MV | ITMC | SDH | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN9800-U32 | MH | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN9800-U32 | MH | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 1A | MH | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 1B | MH | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 1E | MH | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 1F | MH | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16 2A | MH | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN8800-T16- 2B | MH | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
MH-OSN9560 | MH | ITMC | SDH | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30 | The maintenance task shall be assigned to Matara CLS instead of relevant NWEE
Kalutara | KT | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Ambalangoda | AG | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Galle | GL | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Boralesgamuwa | BS | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Keselhenawa | KHN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Meegahathenna | MGE | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Batapola | BTP | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Udugama | UM | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Pitabeddara | PTB | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Kamburupitiya | KJ | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Homagama | HG | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Awissawella | AW | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Rathnapura | RN | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Godakawela | GKW | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Embilipitiya | EMB | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30
Tangalle | TG | ITMC | OTN | 1. check power supply input voltage 2. check power cable connection 3. check grounding resistance 4. check grounding cable connection | High | 2025-01-01 | 2025-06-30