## Sheet1
Node_Name | LEA | Platform | Type | Task | Priority | Start_Date | End_Date | Remark
BLCS Equipment Room_Power | MLV | BLCS | OTN | 1. Check and Record AC Voltage 2. Check and Record AC Current 3. Check and Record DC System 1 Voltage 4. Check and Record DC System 1 Current 5. Check and Record DC System 2 Voltage 6. Check and Record DC System 2Current | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_Rectifier | MLV | BLCS | OTN | 1. Check and Record V-DC 2. Check and Record I-SYS 3. Check and Record I-LOAD 4. Check and Record I-BAT | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS Equipment Room_TEMPERATURE | MLV | BLCS | OTN | 1. Check and Record Temperature of Equipmentt Room 2. Check and Record Temperature of BLCS Battery Room | High | 2025-03-01 | 2025-03-02 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_SLTE | MLV | BLCS | OTN | 1. Check and Record Wave Length & Power level measurement 2. Cleanning of all fan filters of all equipments | High | 2025-03-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_WME | MLV | BLCS | OTN | 1. Check and Record Wave Length & Power level measurement 2. Cleanning of all fan filters of all equipments | High | 2025-03-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_WME | MLV | BLCS | OTN | 1. Check and Record Wave Length & Power level measurement 2. Cleanning of all fan filters of all equipments | High | 2025-03-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_Air Conditioners | MLV | BLCS | OTN | 1. Check the Working Condition of the BLCS Air Conditioners | High | 2025-03-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_AC_UPS Batteries | MLV | BLCS | OTN | 1. Check the Working Condition of the BLCS AC UPS Batteries | High | 2025-03-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_Battery Bank | MLV | BLCS | OTN | 1. Check the Working Condition of the BLCS Battery Bank | High | 2025-03-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_Fire and Temp Sensors | MLV | BLCS | OTN | 1. Check the Working Condition of the BLCS Fire and Temp Sensors | High | 2025-03-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_System | MLV | BLCS | OTN | 1. Check the Sustainability to 5s | High | 2025-03-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_LAND CABLE AND BMH | MLV | BLCS | OTN | 1. Inspection of the BLCS Land Cable Route 2. Inspection of the BLCS Beach Man Hole | High | 2025-03-01 | 2025-03-07 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_Battery Bank | MLV | BLCS | OTN | 1. Discharge Test of the BLCS Battery Bank | High | 2025-01-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_SMW4 Back Up | MLV | BLCS | OTN | 1. Operation of ROP in SMW4 Alcatel/Fujitsu & SN10 Clents | High | 2025-01-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_SPARE Availability | MLV | BLCS | OTN | 1. Check on the Availability of BLCS Spare Inventory | High | 2025-01-01 | 2025-03-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_SYSTEM | MLV | BLCS | OTN | 1.Check and Record readings of the submerged plant parameters of BLCS 2. Performance testing and calibration check of all analysers, measuring equipment and splicing machine | High | 2025-01-01 | 2025-12-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE
BLCS_LAND CABLE AND BMH | MLV | BLCS | OTN | 1. Emptying the beach manhole and take picture. | High | 2025-01-01 | 2025-12-31 | The maintenance task shall be assigned to BLCS instead of relevant NWEE